Sixtieth session

Agenda item 136

Administrative and budgetary aspects of the financing of the 
United Nations peacekeeping operations

Performance report on the budget of the support 
account for peacekeeping operations for the period 
from 1 July 2004 to 30 June 2005

Report of the Secretary-General

Addendum

The present addendum contains information supplementing that found in section II of document A/60/681.

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| II. Resource performance (continued) | 5 |
| Department of Peacekeeping Operations | 5 |
| Executive Office of the Secretary-General | 26 |
| Office of the United Nations Ombudsman | 27 |
| Office of Internal Oversight Services | 27 |
| Office of Legal Affairs | 28 |
| Department of Public Information | 29 |
| Department of Management | 31 |
| Department of Safety and Security | 43 |

Abbreviations

| AU | African Union |
| --- | --- |
| CAA | Civil Aviation Authority |
| ECOWAS | Economic Community of West African States |
| EU | European Union |
| ICAO | International Civil Aviation Organization |
| ILO | International Labour Organization |
| IMF | International Monetary Fund |
| IMIS | Integrated Management Information System |
| MINUCI | United Nations Mission in Côte d’Ivoire |
| MINUGUA | United Nations Verification Mission in Guatemala |
| MINURSO | United Nations Mission for the Referendum in Western Sahara |
| MINUSTAH | United Nations Stabilization Mission in Haiti |
| MONUC | United Nations Organization Mission in the Democratic Republic of the Congo |
| NATO | North Atlantic Treaty Organization |
| NGO | Non-governmental organization |
| ONUB | United Nations Operation in Burundi |
| OSCE | Organization for Security and Cooperation in Europe |
| UNAIDS | Joint United Nations Programme on HIV/AIDS |
| UNAMA | United Nations Assistance Mission in Afghanistan |
| UNAMSIL | United Nations Mission in Sierra Leone |
| UNDOF | United Nations Disengagement Observer Force |
| UNDP | United Nations Development Programme |
| UNFICYP | United Nations Peacekeeping Force in Cyprus |
| UNHCR | Office of the United Nations High Commissioner for Refugees |
| UNICEF | United Nations Children’s Fund |
| UNIFIL | United Nations Interim Force in Lebanon |
| UNIIIC | International Independent Investigation Commission |
| UNIKOM | United Nations Iraq-Kuwait Observation Mission |
| UNLB | United Nations Logistics Base at Brindisi, Italy |
| UNMAS | United Nations Mine Action Service |
| UNMEE | United Nations Mission in Ethiopia and Eritrea |
| UNMIK | United Nations Interim Administration Mission in Kosovo |
| UNMIL | United Nations Mission in Liberia |
| UNMIS | United Nations Mission in the Sudan |
| UNMISET | United Nations Mission of Support in East Timor |
| UNOCI | United Nations Operation in Côte d’Ivoire |
| UNOMIG | United Nations Observer Mission in Georgia |
| UNOPS | United Nations Office for Project Services |
| UNOWA | United Nations Office for West Africa |
| UNSAS | United Nations Standby Arrangements System |
| UNSCO | Office of the United Nations Special Coordinator |
| UNSECOORD | Office of the United Nations Security Coordinator |
| UNTAT | United Nations Training Assistance Team |
| UNTSO | United Nations Truce Supervision Organization |
| WFP | World Food Programme |

II.	Resource performance (continued)

A.	Department of Peacekeeping Operations

1.	Results-based framework

(a)	Office of the Under-Secretary-General

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| 32 reports of the Secretary-General | 66 | 64 reports of the Secretary-General, 1 report on inter-mission cooperation and 1 report of the Special Committee on Peacekeeping. The number of reports has doubled owing to the increase in the number of peacekeeping operations over and above those mandated during the prior reporting period and because of the inclusion of the monthly reporting requirements for Darfur |
| 30 briefings to the Security Council, General Assembly and legislative bodies | 34 |  |
| 55 briefings to Member States and others on peacekeeping | 290 | Briefings and meetings |
| 220 meetings with Member States, regional organizations and groups of friends/contact groups |  |  |
| 150 presentations on peacekeeping issues at conferences, seminars and other public forums | 174 | Presentations |
| 6 published articles/op-ed articles/letters to the editor | 5 |  |
| 75 interviews with and briefings to the media | 50 | Owing to travel of the Under-Secretary-General, the number of interviews was reduced |
| Executive secretariat support to the Special Committee on Peacekeeping Operations | Yes | Including (1) Secretary-General’s 2005 report prepared and circulated to Member States; (2) establishment of matrix on implementation of recommendations for distribution; (3) organization and support for a 4-week 2005 session and a 1-week supplementary session on sexual exploitation and abuse; (4) response to delegates’ queries, provision of updates on progress made with regard to priority issues raised by delegates and provision |
|  |  | of summaries of meetings of the Special Committee on Peacekeeping Operations; (5) support to Chair of the Special Committee, including speaking notes, meeting organization; and (6) informal briefings to the Special Committee on an ongoing basis |

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| 40 meetings with potential troop/police-contributing countries | 25 |  |
| 4 new memorandums of understanding negotiated with Member States for the rapid deployment level of UNSAS | 2 |  |
| Survey/poll conducted on perceptions of peacekeeping in troop-contributing countries/police-contributing countries | No | Survey/poll was not conducted; funding requested was not approved by the General Assembly |
| Implementation of an integrated United Nations planning methodology for complex missions | No | Ongoing Department of Peacekeeping Operations-led inter-agency review due to report to the Policy Committee in late 2005. Revised process provides a more structured approach, with improved integration, clearer lines of responsibility and much enhanced accountability |
| 3 lessons learned studies/after action reports | 6 | Lessons learned studies and analytical papers published |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Integrated Department of Peacekeeping Operations training policy and strategy developed and implemented | No | The integrated training strategy being developed by the Change Management, Training and Evaluation Service/Military Division, Civilian Training and Development Section/Personnel Management and Support Service/Office of Mission Support and the Civilian Police Division was made redundant in 2004/05 by the Under-Secretary-General’s decision to integrate all 3 training components into 1 service. As a result, the Integrated Training Service within the Department of Peacekeeping Operations was established on 1 November 2005, and the strategy is being reworked to reflect the new service organization and responsibilities |
| 2005 heads of mission conference held | Yes |  |
| Implemented improvements identified in the 2003 mission support survey | Yes | Action was taken on all 30 recommendations made in the survey. Of those, 16 have been implemented; the remainder are longer-term initiatives, and action is ongoing |
| Seminar/workshop on cross-cutting themes with mission staff and/or peacekeeping partners | Yes | Knowledge management roundtable for peace operations (New York) Best practices officers and focal point workshop (New York) Annual meeting of gender advisers and gender focal points (New York) Convened and facilitated United Nations rule of law focal point network meetings involving 11 departments and agencies on an as-needed basis (often monthly). Network meetings have served, inter alia, to review system-wide capacities and resources, prepare a draft of a report of the Secretary-General (not issued) and share information on mission-specific rule of law issues in peacekeeping 3-day intensive working group of the network to finalize the draft follow-up report to the Secretary-General’s report on rule of law and transitional justice in conflict and post-conflict societies |
| Survey of troop-contributing countries/police-contributing countries regarding satisfaction and concerns with Department of Peacekeeping Operations planning and support processes | No | Survey was not conducted during the reporting period owing to the surge in peacekeeping activities related to new and expanding missions |
| Revised policies and procedures in the areas of disarmament, demobilization and reintegration, gender and rule of law | No | Policies, guidelines and procedures in the area of disarmament, demobilization and reintegration (known as integrated disarmament, demobilization and reintegration standards: IDDRS) expected to be completed in mid-2006 and to be distributed to peacekeeping missions that are mandated to undertake disarmament, demobilization and reintegration operations Prisons/corrections in peacekeeping policy directive expected to be issued/distributed by January 2006 Draft of policy framework for rule of law/judicial and legal systems to be developed in 2006 Department of Peacekeeping Operations Under-Secretary-General policy statement on gender mainstreaming, which draws on mandates of the Security Council and General Assembly, adopted in March 2005 |
|  |  | Departmental-wide action plan on implementation of gender mainstreaming in peacekeeping developed for Headquarters staff in accordance with a request from the Security Council. Policy recommendations from this process are expected to be adopted by the senior management team of the Department of Peacekeeping Operations in March 2006 and shared with missions by May 2006 |

(b)	Office of Operations

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| 31 multidimensional, substantive reports of the Secretary-General to the Security Council | 65 | 64 reports of the Secretary-General; 1 report on inter-mission cooperation. The number of reports has doubled owing to the increased reporting frequency mandated by the Security Council and because of the inclusion of the monthly reporting requirements for Darfur |
| Letters from the Secretary-General to the President of the Security Council | 57 |  |
| 333 substantive notes for the Secretary-General and for other senior officials’ Security Council presentations | 885 | Substantive notes and talking points Increase in the number owing to the increased reporting frequency mandated by the Security Council, additional briefings requested and inclusion of talking points |
| 34 troop-contributor consultations chaired by the Department of Peacekeeping Operations and by the Security Council with Department of Peacekeeping Operations support | 22 | Troop-contributor consultations chaired by the Department of Peacekeeping Operations |
| 27 oral briefings to the Security Council on issues relating to peacekeeping | 23 | Oral briefings as requested or mandated by the Security Council |
| Background information and advice to the General Assembly and its various bodies on matters related to peacekeeping operations | Yes | Respond to recommendations of, and contribute to briefing and reports for, the Special Committee on Peacekeeping Operations; Fifth Committee; Advisory Committee on Administrative and Budgetary Questions; Committee on Contributions, as requested; Office of Internal Oversight Services, Joint Inspection Unit and Board of Auditors |
| Advice on peacekeeping-related issues provided to permanent missions to the United Nations, United Nations agencies, Bretton Woods institutions, international and regional governance and security organizations and NGOs | Yes | Advice on current and potential peacekeeping operations, mandate implementation, integration and operational needs provided to permanent missions to the United Nations, Office for the Coordination of Humanitarian Affairs, UNDP, UNHCR, UNOPS, UNICEF, WFP, World Bank, IMF, AU, ECOWAS, EU, NATO, OSCE, NGOs and media outlets |

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Integrated concepts of operations for new and potential missions | 1 | UNMIS |
| Updated concepts of operations for ongoing missions | 3 | MONUC (Eastern Division/expansion); MINURSO; UNFICYP |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Guidance and support to 11 missions on operational matters | 14 | Missions, including 2,403 official substantive code cables conveying policy, political, operational and crisis management advice; operational and procedural guidelines for conduct of official functions and mission operations |
| 8 coordinated task forces and working groups with internal/external partners for complex, multidimensional peacekeeping operations | 14 | UNMIL, MONUC, ONUB, UNOCI, MINURSO integrated weekly working groups; UNAMSIL “integrated office” working group, “special court” working group; MINUSTAH Core Group, Integrated Departmental Task Force, Planning Group; UNMEE coordinated working group; UNMIS Working Group, Interdepartmental Task Force; UNMIK privatization group |
| Situation Centre operated 24 hours a day, 7 days a week | Yes |  |
| Situation Centre daily summary and special reports on situation in missions | 251 161 231 | Daily reports Special reports, including weekly updates and background/security assessments Notifications of casualty |

(c)	Office of Mission Support

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| E-platform for Office of Mission Support replicable support models and standard operating procedures | Yes | Prototype completed; target date for implementation is June 2006 |
| Generic job profiles, vacancy compendiums and expert source rosters for filling vacancies in peacekeeping operations | Yes | 26 Generic Field Service job profiles have been approved by the Office of Human Resources Management. The Department of Peacekeeping Operations utilizes existing Office of Human Resources Management-approved generic job profiles for Professional and General Service positions in the field The vacancy compendium (applicable to internal candidates only) was discontinued in July 2004, with the decision to utilize Galaxy and post all vacancies accessible to internal and external candidates. 652 vacancies were posted in Galaxy (429 mission-specific and 223 generic vacancy announcements). Expert source rosters are maintained for 22 occupations |
| Revised contingent-owned equipment manual | No | Achieved in December 2005 The General Assembly, in its resolution 59/298, endorsed the conclusions and recommendations of the Advisory Committee on Administrative and Budgetary Questions and the 2004 Working Group on Contingent-Owned Equipment. The Working Group met in February/March 2004 and a resolution was expected in June or December 2004. However, the resolution was only adopted in June 2005, hence the update and translation of the contingent-owned equipment manual was delayed. The manual has been sent for translation and is expected to be published by 1 May 2006 |
| Contingent-owned equipment and death and disability claims processed within six months and 90 days, respectively | Yes | 915 contingent-owned equipment claims and 84 death and disability claims were certified, respectively |
| Logistics and administration support briefing for troop-contributing countries | 34 | Briefings to troop-contributing countries on logistics and administrative aspects of support to peacekeeping missions |
| Logistics publications and guidelines available to troop-contributing countries | Yes | 26 troop-contributing countries contingents were provided contingent-owned equipment policy/guidance papers through mission contingent-owned equipment units |
| Partnership for Peace conference | No | This output is being reconsidered in the context of competing priorities and reorganization efforts in the Department of Peacekeeping Operations |

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Updated civilian rapid deployment roster | Yes | Completed |
| Mission human resource, logistics and finance checklists and start-up kits | Yes | Finance: including checklists of tasks for the establishment of finance, budget and trust fund management areas in new peacekeeping missions; deployment plans and identified key functions and posts for the establishment of finance, budget and trust fund management areas in new peacekeeping missions; detailed standard operating procedures for the conduct of a technical survey mission by a finance officer to assess local banking facilities, local currency and potential locations for the mission finance section in terms of the physical security of cash, and to discuss status-of-mission agreement issues with government officials |
|  |  | Human resources: including training of all personnel officers in staffing and administrative issues prior to deployment to the field. In addition, all of the guiding human resources principles, reflecting United Nations regulations and rules, are contained, and are regularly updated, in the electronic Department of Peacekeeping Operations Human Resources Handbook, accessible to all field missions |
|  |  | Logistics: including mapping of mission start-up process as guideline/checklist |
|  |  | In addition, establishment of finance systems for new field offices in Burundi, Senegal, the Sudan and the Special Court in Sierra Leone and training of 28 mission staff at start-up in results-based budgeting |
| Validated standard operating procedure on pre-mandate commitment authority | Yes | Pre-mandate commitment authority standing operating procedure updated |
| 3 predeployment training courses for staff on the rapid deployment roster | No | The first course was conducted at UNLB. The other 2 courses were not conducted, as the rapid deployment roster had limited effectiveness. The concept is being revisited |
| Full Office of Mission Support participation in predeployment visits | Yes | 25 predeployment visits were conducted by Office of Mission Support personnel |
| Managed strategic deployment stocks assets to deploy a complex mission readily | Yes | Strategic deployment stocks were effectively used in the deployment of UNMIS, ONUB and MINUSTAH. In addition, strategic deployment stocks equipment was supplied to UNOCI, UNIIC, ESCWA, UNDOF, MINURSO and UNOWA |
| Developed and implemented strategic deployment stocks rotation systems and related administrative procedures | No | The draft for administrative procedures and policy document for rotation of strategic deployment stocks equipment is under review with Department of Peacekeeping Operations senior leadership. The draft will be finalized by June 2006 |
| Modification of strategic deployment stocks based on lessons learned reports | Yes | Replacement items were procured keeping in view the changed operational requirement |
| Trained 90 logistics officers to conduct technical survey, troop-contributing country assessment and predeployment visits | No | The Logistics Support Division was unable to undertake this training owing to overstretch dealing with the surge in peacekeeping activities. This output is being reconsidered in the context of competing priorities and reorganization efforts in the Department of Peacekeeping Operations |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Annual chief administrative officer conference | Yes | Chief administrative officer conference was held at UNLB in May 2005 |
| Standard operating procedures on cost centre/account management | Yes | Cost centre management standard operating procedures on budget preparation, monitoring and reporting. In addition, cost centre guidance on preparation of performance report and closing of accounts was issued |
| Results-based budgeting guidelines published | Yes | Updated |
| Delegation of authority guidelines published | No | Logistics: Draft Property Manual includes guidelines on property delegation and should be issued by December 2005 |
|  |  | Personnel: guidelines were issued to missions with regard to IMIS/human resources implementation and human resources administration, provided in the Human Resources Handbook, which were updated as required |
| Updated/revised field finance manual published | No | Revised manual is scheduled to be issued in November 2005 |
| Mission staffing templates developed | Yes | A medium-sized mission staffing template |
| Updated personnel skills inventory | Yes | The skills inventory module was validated for field deployment through a pilot conducted in UNAMSIL in December 2004. The updated skills inventory will be implemented in all field missions, targeting specific occupational groups, as required, during the first and second quarters of 2006 |
| Updated predeployment personnel checklist | Yes | Completed induction package for staff; piloted the induction training for new staff deploying to the field, held at UNLB; designed and developed a mission readiness package which includes the following: HIV/AIDS in the workplace (UNAIDS); Welcome to the UN System (United Nations Staff College); Basic Security in the Field (Department of Safety and Security), Mission Readiness: Preparing for Field Work (Personnel Management and Support Service/Office of Human Resources Management); Standards of Conduct (Personnel Management and Support Service); and Stress Management (Personnel Management and Support Service). The materials are scheduled to be disseminated to all staff deploying to field operations (including United Nations Volunteers) starting first quarter of 2006 |
| Succession planning framework based on skills inventory data and analysis | Yes | The framework has been developed and is ready to incorporate the skills inventory and mobility roster data. These components are scheduled to be deployed, in a phased manner, to the field missions during the first quarter of 2006 |
| 3 levels of learning development programme for civilian staff implemented | Yes | Priority was focused on development of an overarching civilian training strategy that is now being integrated into an overall Department of Peacekeeping Operations training strategy for all categories of personnel. Concurrently, training efforts were directed to meeting pressing organizational needs and priorities, including induction training programmes for senior leadership and new staff at all levels, management training, e-PAS training and specific skills training, including disarmament, demobilization and reintegration, and press and information |
| Finalized field financial standard operating procedures | No | Standard operating procedures incorporated in the revised Field Finance Manual, which is expected to be issued in November 2005 |
| Memorandums of understanding and inter-agency agreements with peacekeeping partners | 74 | Memorandums of understanding were negotiated with troop-contributing countries |
| Model for standard civilian/military integrated support service structure | No | Draft paper on integrated support service is pending final approval from Department of Peacekeeping Operations leadership |
| Publication of policies and procedures on alternate service delivery | No | Development of policies and procedures on alternate service delivery could not be undertaken owing to overstretch dealing with the surge in peacekeeping activities |
|  |  | This output is being reconsidered in the context of competing priorities and reorganization efforts in the Department of Peacekeeping Operations |
| Rapid recruitment model | Yes | All vacancies are now posted in Galaxy; all recruitment/hiring processing is performed in Nucleus. Field missions have access to view all technically cleared candidates in Nucleus |
| Model for filling vacancies in critical and specialized functional areas | Yes | Personnel Management and Support Service outreach activities to fill critical and specialized functions now also includes advertisement on specialty websites, e.g. ReliefWeb, which provides a direct link to Galaxy for their applicants |
| Model for downsizing/liquidating missions, including the placement of staff | No | The downsizing policy is in its final draft, pursuant to consultation with senior leadership in the field, and will be incorporated into the overall human resources management strategy, which is to be finalized by December 2005. The principles outlined in the downsizing policy have been applied in MINUGUA, UNMISET and UNAMSIL |
| Enhanced field security arrangements | Yes | To enhance the security arrangements in the missions, the Department of Peacekeeping Operations procured security equipment in the amount of $3.6 million on their behalf |
|  |  | The Department of Peacekeeping Operations revised and updated technical specifications of over 55 different equipment/asset items for direct procurement by the missions |
|  |  | In coordination with the Department of Security and Safety, the Department of Peacekeeping Operations conducted a review of security equipment in strategic deployment stocks and initiated the process for the establishment of a 3-year, $5 million security and safety equipment systems contract |
| Support to missions to manage contingent-owned equipment systems and United Nations-owned property effectively | Yes | 4 guidelines on United Nations-owned equipment and 26 policy/procedural guidelines on contingent-owned equipment have been distributed to the field missions |
| Global review of practices and procedures for troop emplacements, rotations and repatriations and contingent-owned equipment movement | No | The global review of practices and procedures for troop emplacements, rotations, repatriations and contingent-owned equipment movement could not be undertaken owing to overstretch dealing with the surge in peacekeeping activities |
|  |  | This output is being reconsidered in the context of competing priorities and reorganization efforts in the Department of Peacekeeping Operations |
| Global mission support medical plan | Yes | Strategic guidance and policies, and logistics frameworks to support 4 level-III hospitals, 17 level-II hospitals and 170 troop-contributing country level-I clinics, catering to more than 700,000 patient visits annually |
| Global fleet management system and spare parts management systems fielded | Yes | Including spare parts conference with participants from African missions, resulting in a number of recommendations to improve fleet management in the field. User requirement on fleet management system updated for off the shelf system to fix shortcomings of Galileo |
| Support to missions to plan, manage and monitor the configuration and utilization of air assets |  | Provided the following support to Missions: • Delivery of aircraft • Certification of invoices • Aircraft specifications, technical analysis and aircraft selection, airfield services and infrastructure • Contract management of aircraft, including presentations to Headquarters Contracts Committee • Aeronautical guidance to ensure mission compliance with Department of Peacekeeping Operations, ICAO and CAA standards • Development of air fleet regionalization and global concept of fleet utilization |
|  |  | • Technical clearance of candidates to fill mission vacancies in air operations • Personnel recruitment guidelines • Mission staffing tables and roster • Training of air operations personnel |
| Published best-practice logistics and operational policies and procedures available to field missions | No | This output is being reconsidered in the context of competing priorities and reorganization efforts in the Department of Peacekeeping Operations |
| Annual vendor performance reviews of goods and services | Yes | 248 aviation contractor performance reports 209 other Department of Peacekeeping Operations contractor performance reports |
|  |  | 254 procurement service annual performance reports (air operations: 93; transport: 161) |
| Updated information and communication technology, plan for business continuity and global systems | Yes | Infrastructure has been created for the transfer and storage of mission critical data for all field missions, including Department of Peacekeeping Operations, headquarters and UNLB. Mission-critical data is backed up on a daily basis at UNLB |
| Logistics contingency planning for 2 new peacekeeping missions | Yes | Planned and launched UNMIS and expansion of UNOCI and MONUC |
| 140 letters of assist certified and managed | 225 | 32 letters of assist certified and managed: 8 supply, 21 air transport and 3 medical support letters of assist |
|  |  | 193 letters of assist claims were certified for payment |
| 180 systems contracts established and maintained | 228 | 79 aviation contracts of variable duration 49 supply systems contracts of variable duration maintained |
|  |  | 4 contracts for geographic information systems supply; high resolution satellite imagery; medium resolution satellite imagery; and geographic information systems software (under establishment) |
|  |  | 42 surface transport systems contracts of variable duration |
|  |  | 29 engineering systems contracts of variable duration |
|  |  | 1 medical support systems contract of variable duration |
|  |  | 24 communication and information services systems contracts established and maintained |
| 120 United Nations-owned equipment movements planned and managed | Yes | Arranged and managed 14 airlift contracts and 10 sealift contracts |

(d)	Military Division

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Daily interchange with representatives of Member States | Yes | Briefings to increase and improve participation in peacekeeping through individual meetings as well as through the forum provided by the military advisers and police community |
|  |  | Liaison to coordinate visits to all missions by military delegations. A total of 833 requests were coordinated |
|  |  | Exchange on notice of casualties and condolence letters |
|  |  | Discussions on follow-up to reports of boards of inquiry and investigation teams |
|  |  | Meetings on training |
| 40 formal and informal troop-contributing countries briefings | 25 | Lower than planned, as many issues were addressed during the daily interactions with the military advisers of the permanent missions. Moreover, where specific matters, such as medical issues, were to be addressed, combined troop-contributing country meetings were conducted. There was greater Department of Peacekeeping Operations integration and concerned Department of Peacekeeping Operations sections addressed the troop-contributing countries at the same time |
| Processes, procedures and equipment interfaces standardized with regional entities and other partner United Nations and non-United Nations organizations | Yes | Including advisory work with AU in an attempt to streamline processes and procedures |
| Military planning advice at peace talks | Yes | Including participation in negotiations associated with the Ceasefire Agreement for the Sudan and assistance in verification of withdrawal of Syrian troops from Lebanon |
| Produce military concepts of operations | 7 | Concepts of operations for UNMIS and revised concepts of operations for the AU mission in Darfur, UNOCI, UNMEE, UNMIL, UNAMSIL and MONUC |
| 2 planning, liaison and advisory teams deployed 3 times to troop-contributing countries | No | This effort was directed to be part of predeployment inspection |
| 15 seminars on utilization of military capacity in peacekeeping operations, with regional organizations, policy centres and think tanks | 15 | Including to EU Political and Security Committee, NATO Defence College, International Association of Peacekeeping Training Centres, AU, Kofi Annan International Peacekeeping Training Centre as well as United States Naval Staff College and Canadian Forces School, by invitation |
| Advice to peacekeeping partners in Africa | Yes | Including participation in RECAMP (Reinforcement of African Peacekeeping Capacity France/AU) in Cotonou and Accra, advice to ECOWAS on transition planning; advice to AU in its planning for Darfur (initial assessment, preparation of concepts of operations, mapping exercise, liaison with international donors) and on forcible disarmament of the Forces démocratiques de libération du Rwanda in the Democratic Republic of the Congo |
| 4 policy papers (Command and Control, Guidelines for Development of Rules of Engagement, Use of Technology and Contractors/Civilianization to Enhance Military Aspects of United Nations Peace Operations, Handbook on Employment of Military Capability in Support of United Nations Objectives) | No | These documents have been incorporated in the Department of Peacekeeping Operations Guidance Project, which is developed by the Peacekeeping Best Practices Section in coordination with all areas within the Department |

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| 50 briefings to potential and current troop-contributing countries on UNSAS and the on-call list | 142 | Targeted briefings to increase the number of troop contributors and the level of their participation |
| 5 predeployment inspections and training needs assessments of troop-contributing countries | 5 | Predeployment visit conducted in 5 troop-contributing countries |
| Military Contributors’ Handbook produced, revised tables of organization and equipment produced and standard operating procedures for handover of military components of a mission to/from the military component of a non-United Nations commanded mission produced | No | Owing to developments on the ground in peacekeeping (e.g. MONUC operations in eastern Democratic Republic of the Congo, MONUC sexual exploitation and abuse) resources had to be reprioritized and allocated to other tasks. Elements of the Military Contributors’ Handbook will be issued as directives, standard operating procedures and guidelines. This is now incorporated in the Department of Peacekeeping Operations Guidance Project |
|  |  | The standard operating procedures for handover of military components of a mission to/from the military component of a non-United Nations commanded mission are in draft form and under discussion with EU |
| 5 peacekeeping training courses/exercises to enhance the rapid deployment capability of troop-contributing countries | 3 | Training conducted in 3 troop-contributing countries with a total of 163 participants |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Ongoing management and administration of individual and contingent deployments, rotations and repatriations | Yes | 2,180 United Nations military observers, and 1,068 staff officers and contingents deployed/rotated individually |
| Assessed military or civilian police component of 4 peacekeeping missions | 4 | UNMIL, MINUSTAH, UNIFIL, UNOCI |
| Predeployment induction and post-appointment briefings for senior military personnel (expect 8) | 23 |  |
| Guidance and advice to heads of field mission military components, through field mission liaison visits to all (12) missions and an annual conference | Yes | Military adviser or senior staff on his behalf travelled to UNOCI, UNMIL, UNAMSIL, MINUSTAH, ONUB, MONUC, UNMIS, UNMEE Participated in the West African Force Commanders’ Conference as part of improving inter-mission cooperation |
|  |  | Assisted UNOCI in electoral process re-evaluation |
|  |  | Organized the military audit team for MINURSO |
|  |  | Conducted annual Heads of Military Components Conference |
|  |  | Special conference organized for UNDOF/UNTSO/UNIFIL |
| Developed standardized training modules, levels II and III, through regional seminars | Yes | The standardized training modules levels II and III have been developed Standardized training modules level-III development included workshops in 4 Member States, 2 peacekeeping missions and a pilot course in 1 Member State |
|  |  | Standardized training modules level-II development included workshops in 7 Member States |
| Produced, translated and distributed standardized generic training module level-I | No | The binder format has been prepared and submitted for printing by ILO. Translation into official United Nations languages has been done. Printing to be completed by February 2006 |
| Lessons learned report produced from existing mission training cells | Yes | The Division instituted a system whereby quarterly reports are submitted from mission training cells and a summary with lessons learned is submitted to senior management for their recommendation |
| Established 3 new mission training cells in new peacekeeping missions | 4 | MINUSTAH, UNTSO/UNDOF, UNIFIL, UNMIS |
| Peacekeeping training publications (produce 1 new, revise 2, translate 1 into all official United Nations languages and reprint and distribute 28 others, as required) | Yes | United Nations Civilian Police Handbook prepared and submitted for printing Revised “Selection Standard and Training Guide for United Nations Military Observers” in all official languages and submitted for printing |
|  |  | Revised “Peacekeeping Training Manual”, “Code of Conduct” and “We are United Nations Peacekeepers” |
|  |  | The complete Training and Evaluation Service publications (28) distributed, as required |
| 6 military peacekeeping training course/seminars for troop-contributing countries | 5 | Peacekeeping course/seminars conducted in 4 Member States and in military and police advisers community, in New York, with a total of 287 participants |
| 3 specific peacekeeping training course/seminars for countries contributing civilian police | 4 | United Nations Police Seminar for senior management held in 3 Member States with a total of 88 participants Police regional UNTAT course, Senegal (26 participants) |
|  |  | 2 Member States conducted their own training to which the Training and Evaluation Service sent presenters |
| 5 training recognition visits to peacekeeping training centres and give presentations at 5 peacekeeping conferences | 6 8 | Training recognition visit conducted in 6 different Member States Presenters/lecturers were sent to peacekeeping conferences in 7 Member States and in MONUC |
| 30 participants from emerging contributing countries in peacekeeping training courses | 77 | Participants, who are mostly from emerging troop-contributing countries and/or African troop-contributing countries, were sponsored by the Department of Peacekeeping Operations when training recognition was conducted by the Training and Evaluation Service, Military Division, in 8 different Member States |

(e)	Civilian Police Division

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Advice to Member States and legislative bodies on policy and procedures regarding police, corrections and judicial matters | Yes | Guidelines on the deployment of individual police officers for UNMIK, UNMIL, UNOMIG, MINUSTAH, UNOCI, UNFICYP, MONUC, UNMIS, UNMISET, UNAMA, UNAMSIL and formed police units for MINUSTAH and UNMIL developed and distributed to 80 Member States |
|  |  | Visits to 4 Member States to meet senior political and police officials to provide advice regarding participation in peacekeeping for police and formed police units |
|  |  | Participated in donors’ conference on Haiti, providing advice on police, corrections and judicial needs |
|  |  | 16 police contributors meetings on UNMIK, UNMIL, UNOMIG, MINUSTAH (2), UNOCI, UNFICYP, MONUC, UNMIS (2), UNMISET (2), UNAMA, UNAMSIL, MINURSO and ONUB |
|  |  | Participated in seminar organized by Amnesty International on United Nations police assistance in post-conflict societies, with participation of Member States and NGOs |
|  |  | Provide on 2 occasions to the military and police advisers community on the strategic mission of United Nations police and recruitment |
|  |  | Invitations to Member States to nominate female police officers for assignment to field missions |
| Quarterly briefings to Member States on police, judicial and corrections issues | 15 | Briefings to Member States on disciplinary issues and legal status of police, formed police units, francophone demand, standing police capacity concept |
| Updated note for guidance distributed to all Member States on UNMIL, UNMIK, MONUC, UNOMIG and UNFICYP | 11 | Guidelines for United Nations police officers on assignment with UNMIK, UNMIL, UNOMIG, MINUSTAH, UNOCI, UNFICYP, MONUC, UNMIS, UNMISET, UNAMA and UNAMSIL completed and distributed to police contributors |
| Selection assistance guideline updated and distributed to all Member States | Yes | Selection assistance guidelines and corresponding training video distributed in French and English to all Member States |
| 25 selection assistance visits to police-contributing countries to provide advice and assist in the selection and predeployment training of police officers | 31 | Selection Assistance Team visits to police-contributing countries assessing 6,450 police, with 2,290 passing, a 35.5 per cent pass rate |
|  | 27 | Special Police Assistance Team visits to formed unit police and K-9 Unit-contributing countries assessing 2,775 formed police officers |
|  | 9 | Predeployment visits conducted to assess unit personnel and inspect contingent-owned equipment |
| Reports to 4 identified African Member States with recommendations to enhance multidimensional police peacekeeping capacity | No | Owing to the surge in peacekeeping operations, resources had to be reprioritized and allocated to other tasks. Expected date of completion is 30 June 2006 |

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Integrated police, judicial and corrections new mission planning guide, which includes a planning check list | Yes | Police planning guide, including a police, corrections and judicial check completed for Department of Peacekeeping Operations planning purpose |
| Report on the analysis of deployments to UNMIL with recommendations to Member States for the improved deployment of police officers | Yes | Reported to Member States on the reasons for the rapid deployment of police (39 days) to UNMIL and provided recommendations for the improved timeliness of future deployments |
| Liaison with regional organizations to develop models for joint assessment, planning, training and rapid deployment | Yes | Liaison with EU on the development of the integrated police unit in MONUC, Darfur and UNMIK Liaison with AU on the planning, deployment and operational aspects of the police peacekeeping in Darfur |
|  |  | Assisted AU in developing AU headquarters capacity, standard operating procedures, job descriptions, and concepts of operation |
|  |  | Participated in International Association of Chiefs of Police European Conference |
|  |  | Participated in South Pacific Chiefs of Police Conference to discuss issues of participation in peacekeeping, training and rapid deployment |
|  |  | Participated with the United States Institute of Peace and the Center of Excellence for Stability Police Units on a formed police unit workshop |
|  |  | Collaborated with EU and its Member States on rule of law training |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Guidelines for the vetting and telephonic skill-based interview of police and corrections officers | Yes |  |
| Predeployment induction and post appointment briefings for senior police and correction officials for UNMIK, UNAMSIL, MONUC and UNMIL Predeployment management training guidelines and curriculum for police- contributing countries | 7 Yes | Inductions for MONUC, UNMIK, MINUSTAH, UNMIS, UNMIL, ONUB and UNFICYP Including broad working-level consultations within the Department of Peacekeeping Operations, with representatives of the Member States, United Nations agencies and programmes and peacekeeping missions 23 police-contributing countries received predeployment training |
| Training standards and guidelines for formed police units for Member States | Yes |  |
| Recruited and provided the administrative management of the individual rotations, repatriations and extensions of 4,600 police officers and 120 corrections officers | 3 213 2 775 73 | Individual police officers Formed police unit personnel Corrections officers |
|  |  | Recruited 5 police experts to assist MINUSTAH in developing the reform and restructuring plan for the Haitian national police |
|  |  | Provided technical assistance by developing vacancy announcements, sending notes verbales to permanent missions, screened applications and conducted interviews for the MONUC sexual exploitation investigations team |
|  |  | Provided technical assistance by developing vacancy announcements, sending notes verbales to permanent missions and screening applications for the Department of Political Affairs-led Hariri investigative commission |
| Induction manual for corrections officers | No | Owing to the surge in peacekeeping, the task had to be reprioritized, with the only corrections officer of the Department of Peacekeeping Operations focused on other tasks. A final draft will be ready in February 2006, with a final edited version completed by May 2006 |
| 20 judicial and corrections officer job descriptions developed | 20 | 5 corrections and 15 judicial job descriptions have been developed |
| Judicial and corrections officer database of 100 officers | No | Owing to the surge in peacekeeping, this task had to be reprioritized, with staff allocated to other tasks. The database or lists of eligible judicial and corrections officers will be compiled within the new Personnel Management and Support Service roster system, rather than developed as a separate or competing database. This streamlined approach will be more efficient and effective. The databases will include a total of 100 judicial and corrections officers by early 2006 and will continue to be refined thereafter |
| Training programmes on code of conduct and discipline conducted in the field missions for police and corrections officers for UNMIL, UNMIK and UNAMSIL | Yes |  |
| Desk officer operational missions to UNMIL, UNMIK, UNMISET, MONUC, UNOMIG and UNFICYP to advise mission on mandate implementation and review best practices | 16 | Visits to police components in UNMIL, UNMISET (2), UNMIK (2), UNOMIG, UNFICYP, MONUC (2), UNOB (2), MINUSTAH (3) and UNOCI (2) Inspector General assessment reports on UNOCI, UNMIS and MINUSTAH |
| Best practices workshops on vetting of local police officers’ peacekeeping operations and the deployment and recruitment of civilian police officers | No | Owing to the surge in peacekeeping resources had to be reprioritized and allocated to other tasks. Expected date of completion is January 2006 |
| United Nations model for community policing | Yes | The model, training programme and process for implementation have been shared with the 13 police components |
| Conflict resolution training for police in peacekeeping operations for use during mission induction training | Yes | Training modules developed and distributed to UNMIK, UNMIL, UNOMIG, MINUSTAH, UNOCI, UNFICYP, MONUC, UNMIS, UNMISET, UNAMA, UNAMSIL, MINURSO and ONUB |

(f)	Mine Action Service

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Updated mine action rapid response plan | Yes | The revised United Nations Framework for Mine Action Planning and Rapid Response was approved by the Inter-Agency Coordination Group for Mine Action principals, chaired by the Under-Secretary-General for Peacekeeping Operations |
| Standby agreements in place to provide mine action capacities | Yes | A memorandum of agreement between UNMAS and UNOPS to implement the Framework for Mine Action Planning and Rapid Response is in place. An independent evaluation of the Rapid Response Plan, following its implementation in Iraq in 2003, concluded that it is more advantageous to utilize an emergency tendering process through UNOPS. This will enable the capacities to be tailored to suit the requirements of the situation, rather than utilizing fixed agreements that specify the capacity to be provided |
|  |  | An agreement between UNOPS and the Swedish Rescue Services Agency for logistical and communications support to a coordination team is in place |
| Funds identified and earmarked to enable deployment of rapid response plan | Yes | A total of $1.366 million has been mobilized and is earmarked in the Voluntary Trust Fund for Assistance in Mine Action for the deployment of fact-finding and coordination teams and for the mobilization of operational capacities |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Updated annual local, national and organizational project proposals in UNMEE, MONUC, UNFICYP and UNIFIL | Yes | Completed for all missions |
| Evaluation reports of UNIFIL mine action programme | No | An evaluation was completed of the UNMEE mine action programme instead of UNIFIL |
| Country-specific plans developed for the phasing and devolution of mine action programmes to national authorities for UNIFIL and UNMEE | No | The situation that exists in these missions is not conducive to detailed transition planning |
| Production of materials and coordination of landmine safety briefings in mission areas | Yes | Developed and distributed additional landmine safety training materials: Kosovo leaflet updated; CD-ROM in 4 languages for trainers, with various training aids, including PowerPoint presentations; promotion posters in 7 languages. Materials provided to MONUC, ONUB, UNIFIL, UNMEE, UNMIS and MINURSO |
|  |  | Provided training of trainer workshops for MONUC (4 and 5 October 2004) |

B.	Executive Office of the Secretary-General

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Comments and guidance to missions or the Department of Peacekeeping Operations on Secretary-General’s mission reports | Yes | Including 468 letters, 96 reports and 752 notes to the Department of Peacekeeping Operations and peacekeeping missions |

C.	Office of the United Nations Ombudsman

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| 120 cases resolved | Yes | 133 staff members sought the assistance of the Office in the reporting period |
| Guidance, advice and support provided to civilian mission personnel on prevention of disputes | Yes | All missions have been connected to the website link of the Ombudsman, with access to the contact form for submitting complaints and receiving advice on conflict resolution Information on the role of the Office of the Ombudsman in conflict prevention and resolution has been prepared for incorporation in the induction materials going to new recruits for peacekeeping missions A video called “Meet the Ombudsman”, explaining the role of the Ombudsman in conflict resolution, has been produced and sent to missions for incorporation into the orientation programme for new mission arrivals |

D.	Office of Internal Oversight Services

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| 2 inspection reports to the General Assembly | 1 | Report on review of operational capacity of United Nations military observers. Lower number because horizontal audits on cross-cutting issues required additional resources (audit of field security management and audit on state of discipline in peacekeeping operations) |
| 3 General Assembly reports plus additional reports that may be requested by the Assembly | 1 | Report on review of operational capacity of United Nations military observers |
| 70 completed investigations | 67 | Lower number owing to sexual exploitation and abuse cases investigations (unplanned) in MONUC required resources |
| 40 investigation reports issued | 67 | Higher number owing to investigation reports on sexual exploitation and abuse cases |
| 20 referrals to relevant programme managers for comment and action prior to Office of Internal Oversight Services investigation | 55 | Higher number owing to improved referrals management service in Investigations Division |
| 20 advice and service requests provided | 86 | Higher number owing to improved referrals management service in Investigations Division |
| 10 audit reports by United Nations Headquarters auditors | 8 | Lower number because 4 out of 8 reports were presented to the General Assembly, generally reports issued to heads of department; detailed planning for some resident audits was conducted at Headquarters requiring involvement of Headquarters auditors |
| 42 audit reports by resident auditors located in peacekeeping missions | 60 | Higher number because detailed planning for some resident audits was conducted at Headquarters, resulting in increased staff time for audits/reports by resident auditors |
| 6 risk assessment exercises by resident auditors in peacekeeping missions | 6 | In MONUC, UNAMSIL, UNMEE, UNMIK, UNMIL and UNMISET |
| 2 horizontal audits of systemic, cross-cutting issues | 2 | Audits on “Field Security Management” and “Management of Rations Contracts” |
| 20 resident auditors participated in professional development training plus 1 annual meeting of resident auditors | 20 | Resident auditors trained at UNLB; in addition, 1 annual meeting in New York |

E.	Office of Legal Affairs

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Legal support and assistance through the provision of legal opinions and advice to all peacekeeping operations on an as-needed basis, regarding: |  |  |
| 50 legislative aspects of peacekeeping missions, including governance issues and United Nations regulations and rules | 239 | Higher number owing to the surge in peacekeeping |
| 100 institutional and operational arrangements for peacekeeping missions (e.g., status-of-forces agreements, status-of-mission agreements and other similar agreements as well as general questions of public international law and rules of engagement) | 189 | Higher number owing to the surge in peacekeeping |
| 195 commercial aspects of peacekeeping missions | 543 | Higher number owing to the surge in peacekeeping |
| 25 claims arising out of peacekeeping missions, including arbitration or litigation of claims and representation in cases before the United Nations Administrative Tribunal | 37 | Higher number owing to the surge in peacekeeping |
| 15 financial questions arising in connection with peacekeeping missions | 37 | Higher number owing to the surge in peacekeeping |
| Maintaining 50 privileges and immunities of the United Nations and its peacekeeping operations | 82 | Higher number owing to the surge in peacekeeping |
| 75 personnel matters, including staff regulations and rules | 157 | Higher number owing to the surge in peacekeeping |
| 20 legal aspects of security within the missions | 37 | Higher number owing to the surge in peacekeeping |

F.	Department of Public Information

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Pre-mission assessments of public information requirements and capacity in the field and support to rapid deployment public information staff of new peacekeeping missions | Yes | Backstopping for newly created peacekeeping missions — UNOCI, ONUB, MINUSTAH and UNMIS, including guidance in developing communications strategies, budget preparation, staff identification and recruitment No pre-mission assessments required |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Strategic guidance and support, from Headquarters and in situ, to 5 complex peacekeeping operations (MONUC, UNMEE, UNMIL, UNMIK and UNOMIG) in formulating and implementing information strategies reflecting global priorities in peacekeeping | Yes | In addition, guidance to UNAMSIL and UNMISET, and 4 other complex peacekeeping operations — MINUSTAH, ONUB, UNMIS and UNOCI On-site visits to MINUSTAH, UNMIK, UNMIL, UNOCI and UNOMIG to support implementation of the public information plan of action |
| Advice on strategic communications to 4 peacekeeping operations (MINURSO, UNDOF, UNFICYP and UNIFIL) | Yes | No advice required for UNDOF, since the mission has neither a civilian public information office nor an active public information programme |
| Maintained 7 web pages each for 11 current United Nations peacekeeping missions | Yes | For 14 peacekeeping operations (average of 7 web pages each) in United Nations Headquarters peacekeeping page, including MINURSO, MINUSTAH, MONUC, ONUB, UNAMSIL, UNDOF, UNFICYP, UNIFIL, UNMEE, UNMIL, UNMIS, UNMISET, UNOCI and UNOMIG In addition, public information materials from 10 peacekeeping missions (MINUSTAH, MONUC, ONUB, UNAMSIL, UNMEE, UNMIL, UNMIS, UNMISET, UNOCI and UNOMIG), technically prepared and posted Other Department of Public Information-maintained portions of United Nations peacekeeping and Department of Peacekeeping Operations sites maintained, developed or expanded |
| Conducted a 1-week specialized training course for public information rapid deployment team | Yes | Organized a rapid deployment training course for 26 public information officers from peacekeeping missions |
| Updated standard operating procedures for public information components | Yes |  |

G.	Department of Management

1.	Results-based framework

(a)	Office of the Under-Secretary-General

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Rendered 29 decisions on behalf of the Secretary-General on recommendations made by Joint Appeals Board and Joint Disciplinary Committee and monitored the implementation of the United Nations Administrative Tribunal judgements in respect of peacekeeping mission staff | 31 | Decisions on behalf of the Secretary-General on recommendations made by the Joint Appeals Board and the Joint Disciplinary Committees rendered and the implementation of the United Nations Administrative Tribunal Judgements in respect of peacekeeping mission staff monitored |
| Implemented 29 Secretary-General’s decisions on appeals and disciplinary cases in respect of peacekeeping mission staff | 31 | Secretary-General’s decisions on appeals and disciplinary cases in respect of peacekeeping mission staff implemented |
| Updated the electronic Case and Jurisprudence Digest of Judgements of the United Nations Administrative Tribunal | Yes | 51 judgements rendered by the Tribunal during the period were entered in the electronic Case and Jurisprudence Digest of Judgements of the United Nations Administrative Tribunal |

(b)	Office of Programme Planning, Budget and Accounts

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Contributions Service |  |  |
| Ad hoc reports and advice to the General Assembly on peacekeeping assessments | Yes | Information on status of contributions to peacekeeping operations provided for the Advisory Committee on Administrative and Budgetary Questions and Fifth Committee |
| Monthly detailed report on the status of contributions | 12 |  |
| Monthly informal summaries of outstanding assessed contributions | 12 |  |
| Bimonthly informal summaries of the status of contributions of the 15 major contributors and other Member States | 24 |  |
| Peacekeeping Financing Division |  |  |
| 20 reports on budget performance and budget estimates for 10 active missions | 37 | For 15 active missions |
| 1 report on updated financial position for 16 closed missions | 1 |  |
| 4 reports on final performance and disposition of assets of 2 liquidated missions (UNMIBH and UNIKOM) | 2 | Final performance report for UNIKOM deferred to the 60th session owing to the need for additional technical/substantive consultations |
| 8 reports and notes on administrative and budgetary aspects of the financing of United Nations peacekeeping operations, including the support account and the UNLB | 13 | Including 2 statements submitted by the Secretary-General in accordance with rule 153 of the rules of procedure of the General Assembly on the programme budget implications of draft resolutions A/C.4/59/L.20 and A/C.5/59/L.53 |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Treasury |  |  |
| Investment and cash management reports for peacekeeping mission (approximately 250 daily reports, 12 monthly reports and 2 semi-annual reports) | Yes |  |
| 1,400 electronic fund movements, 280 foreign exchange purchases, and 2,000 investment settlements for peacekeeping missions per annum. Reconciled cash balances and investments daily. Prepared monthly and semi-annual investment accounting reports | 2 819 | Electronic fund movements, for total value of $8.8 billion |
|  | 454 | Foreign exchange purchases, for total value of $748 million |
|  | 1 511 | Investment settlements |
| Payments to peacekeeping missions, international peacekeeping personnel, troop-contributing countries, Member States and others | 70 000 | Payments for total value of $2.5 billion, excluding internal cash transfers |
| Initiated and tested implementation of SWIFT software, a new Headquarters payments system and cash management system to extend Overseas Private Investment Corporation functionalities | Yes |  |
| Implemented and tested Treasury disaster recovery plan | Yes | Implemented for DC-1, but failed during a major power outage |
| Implemented 2 new peacekeeping mission payments systems (UNMEE, UNMIL) | 2 | In UNMEE and UNOMIG; UNMIL planned for end of 2005 |
| Assessed, advised and assisted peacekeeping mission personnel in cash management functions, Treasury policies, procedures and best practices (UNMEE, UNMIL, UNDOF and MINURSO) | Yes | In UNMEE, UNDOF, UNMIL, UNOCI and MONUC; MINURSO accomplished in 2003-2004 |
| Revised instructions for offices using banknotes in conjunction with UNSECOORD | Yes | Issuance of the instructions by the Department of Safety and Security (previously UNSECOORD) scheduled for October 2005 |
| Training of chief finance officers in peacekeeping missions on Treasury policies and procedures | No | Scheduled for latter half of 2005 |
| Contributions Service |  |  |
| 55 notifications of assessments and credits for peacekeeping operations | 61 |  |
| 10 assessment documents for peacekeeping operations | 16 | With the issuance of these, the backlog has been eliminated |
| Annual comprehensive reminder to Member States regarding unpaid assessments | 2 | Issued in late 2004 and an extra reminder sent in May 2005 |
| 2,200 receipts for contributions from Member States for peacekeeping operations | 2 515 |  |
| Annual notification of Member States liable to fall under Article 19 of the Charter of the United Nations | 1 |  |
| Peacekeeping Financing Division |  |  |
| Payment letters to troop-contributing countries and formed police-contributing countries | Yes |  |
| Funding authorizations issued on an ongoing basis for missions and peacekeeping trust funds | Yes |  |
| Issued mission staffing table authorizations | Yes |  |
| Financial reports issued to Member States for peacekeeping trust funds | Yes |  |
| Updated methodology for budget management autonomy | No | Not implemented owing to capacity constraints resulting from the surge in peacekeeping |
| Policy guidance to missions on budget formulation and implementation in situ and from Headquarters | Yes |  |
| Trained 235 cost centre managers in peacekeeping missions on phases I and II (upgrade) of the funds monitoring tool and 190 mission staff on the automated data collection tool, for automated data collection and monitoring of the results-based frameworks | 121 | Owing to competing work priorities, the lower number resulted from the cancellation of planned funds monitoring tool training of personnel from UNDOF, UNFICYP, UNIFIL, UNMEE and UNMIS. The total includes 3 ONUB staff, who were trained during the mission visit for the period from 1 to 5 November 2004. Planned training on the automated data-collection tool was cancelled owing to its incorporation into the Division’s enterprise budgeting application system |
| Accounts Division |  |  |
| 3 consolidated and 38 individual financial statements with 18 schedules, based on processing approximately 275,000 accounting transactions as well as review, analysis and consolidation of field accounts | 3 | Consolidated financial statements |
|  | 40 | Individual financial statements |
|  | 18 | Schedules |
|  |  | Based on 351,253 accounting transactions |
|  |  | Higher number owing to new missions |
| 10-15 ad hoc interim financial statements for liquidated missions | No | Not required, reports on fiscal year-end statements used instead |
| High-level policy guidance to peacekeeping operations on financial regulations, rules, accounting policies and insurance matters | Yes | Including, in cooperation with the Department of Peacekeeping Operations, field finance procedures guidelines partially updated; insurance coverage issues/options related to daily workers in peacekeeping missions assessed; chief administration officers’ delegations of authority document/guidance updated/developed on accounting issues |
| Advice and guidance to missions and the Department of Peacekeeping Operations on accounting and insurance issues | Yes | Including guidance and procedures on the recording of strategic deployment stocks transactions in IMIS Field accounts reviewed and monitored monthly to interpret and consistently apply accounting policies; audit findings reviewed to provide guidance on appropriate actions to enable compliance with recommendations Advice on review of obligations and non-expendable property issues, including reporting requirements Guidance on insurance provisions and claims in vendor service contracts |
| Approve approximately 15,000 payments to Member States, staff and vendors | 18 279 | Higher number owing to the increased number of missions |
| Negotiate 7 peacekeeping insurance coverages | 10 | Including insurance coverage for malicious acts insurance policy and 2 policies covering Department of Peacekeeping Operations property at United Nations Headquarters |
| Provide health and life insurance coverage to approximately 8,954 peacekeeping staff | 4 340 | International staff, representing 9,678 insured lives, including dependants. Insurance for national staff through the United Nations medical insurance plan administered locally Higher numbers owing to new missions |
| Settle all insurance claims and Advisory Board on Compensation Claims claims | 75 | New compensation claims reviewed |
|  | 40 | Insurance claims processed and/or settled under the master aviation, malicious acts and worldwide vehicle insurance policies |
| Improve processes related to accounting, insurance and disbursements, such as standardized strategic deployment stocks procedures and automated travel claim procedures | Yes | Strategic deployment stocks procedures approved by Controller in August 2004 Malicious acts insurance policy claims procedures standardized and improved Meetings held with the Department of Peacekeeping Operations and insurers towards utilization of an insurance website to enable decentralization of declaration and payment for shipments under the ocean cargo insurance policy A portal for staff members to enter travel claims data developed |

(c)	Office of Human Resources Management

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Operational Services Division |  |  |
| Reviewed classification requests | 150 | Requests reviewed |
| Issued vacancy announcements | 82 | Including 18 vacancy announcements for military and civilian police positions transmitted to Member States through notes verbale |
| Pre-screened qualified candidates for filling vacancies in the Department of Peacekeeping Operations at Headquarters | 1 150 | Applications (hard copy) for military and civilian police positions pre-screened; data on 117 applicants entered in Galaxy for further review by the programme manager |
|  | 20 000 | Applications (Galaxy and hard copy) for non-military and civilian police pre-screened |
| Extended and recruited personnel of all types in the Department of Peacekeeping Operations at Headquarters | 86 | Initial appointments |
|  | 134 | Reappointments |
|  | 625 | Extensions |
|  | 129 | Separations |
| Certified chief administrative officers and chief civilian personnel officers for missions | 45 |  |
| Implemented human resources delegated authority monitoring system and its tools, including on-site visits to 11 missions | 1 | On-site visit to MINUSTAH; terms of reference for use in future monitoring missions reviewed and refined; on-site visits planned for UNMIS, ONUB and MINUSTAH in the 2005/06 cycle Low number of on-site visits owing to staff turnover in the responsible work unit |
| Guidance and support to the Department of Peacekeeping Operations and to missions on human resources management in the field, including rules and regulations management | Yes | Guidance on a daily basis to the Department of Peacekeeping Operations (7 per requests/day on average) Support to Department of Peacekeeping Operations staff members (537 on support account posts) Support to mission staff in areas not delegated to the Personnel Management and Support Service/Department of Peacekeeping Operations, including movement of mission staff to higher level, agreed termination, disability, career development/mobility |
| Division for Organizational Development |  |
| Managed requests for administrative review, appeals and disciplinary cases in respect of civilian mission personnel (45-50 formal cases and ongoing advice) | 35 1 | Requests for review conducted, including preparation of review letters in certain cases Respondent at 1 suspension of action hearing represented |
|  | 4 | Respondent replies to the Joint Appeals Board prepared and submitted |
|  | 26 | Disciplinary cases revised and advised on, including representation of the administration before the Joint Disciplinary Committee |
| Advice and lessons learned on administration of justice matters for missions | Yes | Ongoing consultations with the Department of Peacekeeping Operations and peacekeeping missions on appeals, disciplinary and other human resources issues, and provision of input into the preparation of guidelines for the implementation of the policy on sexual exploitation and sexual abuse |
| Guidance and support to the Department of Peacekeeping Operations on human resources management in missions, including rules and regulations management | Yes | Recommendations aimed at harmonizing contractual arrangements and conditions of service of field staff developed. 7 generic job profiles for field service jobs finalized and promulgated |
| Reviewed/updated policies on relevant entitlements for all civilian mission personnel | Yes | Guidelines for movement of mission staff to higher level posts and for determination of level and step on recruitment to the Professional category and above updated |
| Comprehensive salary surveys (3) and salary scales issued (80) for local staff in peacekeeping missions | 3 | 3 surveys (UNMEE, UNMISET, UNMIK) |
|  | 18 | Scales for 100-series staff |
|  | 8 | Scales for staff on appointments of limited duration |
|  | 64 | Updated scales |
| Mission subsistence allowance rates and policies on entitlements reviewed in 8 peacekeeping missions | 7 | UNDOF, UNIFIL, MINUSTAH, UNMISET, UNAMIL, UNOMIG, UNAMSIL |
| Headquarters staff counselled on mission readiness prior to departure, including participation in mission readiness briefings (12 sessions), and debriefed upon return | Yes | Individual sessions for departing and returning staff members conducted. New P-3 staff counsellor started in April 2005. Mission readiness workshop being designed |
| Guidance and advice to offices away from Headquarters on setting up mission readiness services for their staff selected for mission assignments | No | Mission readiness programme operational guidelines for the field offices being developed. New P-3 staff counsellor started in April 2005 |
| Support services offered to families of Headquarters staff on mission (approximately 200 interventions) | No | Identification of the family support programme components in progress. New P-3 staff counsellor started in April 2005 |
| Revised and distributed material on mission readiness (5 missions) | Yes | Mission readiness booklets are printed and a total of 5,000 copies have been sent to the Department of Peacekeeping Operations for distribution to missions |
| Developed and phased delivery of the mission readiness programme (predeployment, on-arrival, career development and post-deployment components) in 5 field missions | No | Implementation delayed to 2005/06. Discussions were held with the Department of Peacekeeping Operations about the use of Department mission staff counsellors in conjunction with the staff counsellor at Headquarters for this activity |
| Customized and conducted performance management, e-PAS and competency training and follow-up programmes in 6 missions | 6 | UNIFIL, UNAMSIL, UNMEE, MONUC, MINURSO, UNMIK |
| Developed and conducted a pilot work planning programme in 2 key missions | No | It was agreed to defer this activity, as the Department of Peacekeeping Operations had not yet completed the Integrated Mission Planning Process (IMPP). This element is a pre-requisite for the work planning activity |
| Conducted customized supervisory skills programmes for General Service and Professional staff in 5 field missions | 7 | UNIFIL, UNAMSIL, UNMEE, MONUC, UNDOF/UNTSO/UNSCO, MINURSO, UNMIK |
| Medical Services Division |  |  |
| Updated health policies related to staff protection from potential biological, chemical and nuclear threats for all mission personnel, including civilian and military component, and maintained readiness to respond to such events | Yes | Health policies, medical standards and mission-specific guidelines and procedures formulated for newly established missions, i.e. UNOCI, ONUB, MINUSTAH, and UNMIS HIV/AIDS (voluntary and confidential counselling and testing) policy and treatment guidelines updated |
| 5 on-site reassessments of mission medical facilities (UNMIL, UNAMSIL, and MONUC) | 2 | In UNMIL, all troop-contributing country hospitals, United Nations-owned medical clinics and local medical facilities assessed; in MONUC, all troop-contributing country hospitals, United Nations-owned medical clinics and local facilities assessed; UNAMSIL covered in evaluations of 1 of its possible regional medical evacuation centres |
| 5 evaluations of regional medical evacuation centres linked to peacekeeping missions (Nairobi, Johannesburg, Cairo and Dubai) | 1 | Evaluation visit to Accra to assess its use as a regional medical evacuation centre for UNMIL and UNAMSIL. Nairobi was evaluated in June 2004 and Johannesburg, Cairo and Dubai evaluation visits are being planned in 2005/06 |
| Adapted mission-specific health-related internal and external guidelines and procedures for all physicians of the United Nations system and those of troop-contributing countries for 11 missions | Yes | Immunization and personal protection guidelines updated for 16 peacekeeping missions |
| Ongoing technical support to 10 established United Nations civilian medical facilities in mission areas | 33 | Medical facilities. Higher number owing to increased number of civilian clinics in large missions |
| Updated roster of physician candidates for mission assignment | Yes | Curricula vitae of 277 physician candidates (P-5, P-4, P-3 posts) reviewed, out of which 67 cleared; curricula vitae of 207 United Nations Volunteers physician candidates reviewed, out of which 97 cleared |
| Medically examined 400 candidates for mission deployment | 475 | Higher number owing to new missions |
| Pre-mission briefing and consultation (1,500) | 2 000 | Higher number owing to new missions |
| Pre and post-mission psychological assessment (300) | 450 | Higher number owing to new missions |
| Mental health management, including diagnosis, therapy, outside referral and follow-up (600) | 600 |  |
| Administered 1,700 immunizations for mission deployment | 1 554 | Immunizations provided at United Nations Headquarters |
| Issued 1,500 medical kits for mission travel and deployment | 1 989 | Higher number owing to new missions |
| Medical treatment and consultations to Department of Peacekeeping Operations Headquarters staff and those visiting from missions | 4 612 | Consultations by nurses |
| Post-mission advice on service-incurred illness/injury (20) | 16 | Cases |
| Reviewed and analysed 6,000 medical exams of mission staff, military observers and civilian police to determine fitness for recruitment/assignment/travel | 8 752 | Higher number owing to new missions |
| Certified sick leave for 6,000 mission and Department of Peacekeeping Operations staff | 5 216 | For all Department of Peacekeeping Operations staff, military observers and civilian police |
| Advised United Nations Joint Staff Pension Fund on disability pensions for mission staff (60) | 79 | Disability pension cases of Department of Peacekeeping Operations staff presented to Staff Pension Committee |
| Advised and assisted in 500 medical evacuations/repatriations from all missions | 819 | Cases reviewed for mission staff, military observers, civilian police and troops |
| Advised on medical compensation through the Advisory Board on Compensation Claims for 300 civilian staff, military observers and civilian police | 354 | Cases presented (54) to Advisory Board on Compensation Claims; Advisory Board advised of decisions (354) made in these cases as well as ongoing cases |
| Advised on 100 troops’ death and disability claims from all missions | 50 | Claims reviewed |
| Maintained medical database for ongoing health promotion programmes for 6,000 mission staff | Yes |  |

(d)	Office of Central Support Services

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Archives and Records Management System |
| Archival records identified on-site at UNMEE, UNMIL and UNOCI for immediate or future transfer to Headquarters, New York, for preservation and research use by the Organization and Member States | No | Completed at UNMIL and UNMISET; UNMISET postponed from 2003/04 4,000 megabytes of digital records accessioned from UNIKOM |
| Reference responses to the Organization and Member States for access to peacekeeping archives (approximately 1,037 requests per year) | 958 |  |

| Expected accomplishment 2: reduction of the time required to plan, rapidly deploy and establish peacekeeping operations in response to Security Council mandates |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Procurement Division |  |  |
| New system contracts issued and purchase orders against these and existing system contracts issued within 14 days upon receipt of funded requisitions to replenish goods and necessary follow-up with vendors to ensure timely delivery of correct equipment and services in support of strategic deployment stocks | No | 61 system contracts issued and 401 purchase orders issued against system contracts within 42.5 days on average |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Archives and Records Management System |
| Tailored records management programmes for UNMEE, UNMIL and UNOCI, including policy and procedures manual, recordkeeping metadata standard, training materials, retention schedule and file classification scheme | No | Completed in UNMIL and UNMISET In addition, compliance with Security Council resolution 1599 (2005), complete copy of Timor-Leste’s Serious Crimes Unit archived at Headquarters |
| Facilities Management Division |  |  |
| Delivered incoming mail and pouches | Yes |  |
| Information Technology Services Division |  |
| Supported 16 satellite links and 400 related dedicated voice and fax channels for 24 hours a day/7 days a week connectivity to 11 missions | Yes | 29 satellite links and connectivity to 15 missions supported |
| Supported Intranet and IMIS connectivity to 11 missions in 16 different locations | Yes | Intranet connectivity to 15 missions, hosted in 17 locations |
| Maintained and supported United Nations Headquarters and mission crypto units (54) | Yes | A total of 228 crypto units are supported and maintained (120 for voice and 108 for fax) |
| Travel and Transportation Service |  |  |
| Negotiated special airline travel agreements for movements of 20 or fewer peacekeeping staff | 26 | Airline agreements with discounts well above industry benchmarks |
| 5,000 inspected travel authorizations | 7 881 |  |
| 3,500 lump-sum travel requests | 3 832 |  |
| 5,500 issued United Nations travel documents and visas | 8 089 |  |
| 4,500 processed shipping-related documents | 3 613 | Personal effects shipments, including insurance claims |
| 7,000 received/delivered pieces of goods, materials and parcels | 8 956 |  |
| Office supplies ordered through the Department of Peacekeeping Operations at Headquarters shipped to 3 peacekeeping missions | Yes | Supplies related to 679 stock requisitions provided to the Department of Peacekeeping Operations |
| Procurement Division |  |  |
| 510 contracts awarded (including amendments to contracts), 1,400 purchase orders issued and 115 system contracts (including amendments to contracts) placed for all missions | 472 | Contracts |
|  | 2 475 | Purchase orders |
|  | 170 | System contracts. Higher number owing to new and expanding missions |
| Procurement management reviews conducted in UNMIL, MINUCI, MONUC, UNMEE, UNIFIL, UNMIK, UNFICYP, MINURSO and UNLB | 4 | In UNMIL, UNOCI and UNMIS; technical support visit to UNLB; management reviews of the other missions will be considered in 2006, while priorities will be given to new and expanding missions |
| 150 staff trained in procurement through the training sessions in UNMIL, MINUCI, MONUC, UNMEE, UNLB and UNFICYP | 170 | In UNMIL, UNOCI, MINUSTAH, UNMIS and ONUB; participated in training organized locally by UNMEE. Priority given to new missions. Staff of UNLB and MONUC attended the training in the first half of 2004. Training of staff of UNFICYP as well as all these missions will be considered for the common procurement training programme to be implemented in 2006 |
| 30 staff from the field missions and the Logistics Support Division trained at United Nations Headquarters | 18 | Chief procurement officers of 18 (peacekeeping and special political) missions trained during chief procurement officers conference |
| Technical advice given for complex procurement issues for all missions | Yes | Including start-up of UNMIS |
| Streamlined and improved procurement procedures, process and development of tools, such as revised delegation of procurement authority, definition of “core” products and services to be completely delegated for local procurement and procedure for clearance of local procurement, to facilitate field procedure | Yes | The revised delegation of procurement authority document issued |
| 70 local procurement cases from the field missions reviewed and presented to the Headquarters Committee on Contracts within 10 working days of receipt | 41 | Cases, out of a total of 178 submitted cases, presented to the Committee on Contracts within 10 working days Lower number because many local procurement cases required clarification from the field missions |
| Mercury system installed and implemented at Headquarters | No | It has taken more time to review and develop technical requirements in consultation with all stakeholders. Implementation is expected by the end of 2006 |
| Internet-based common vendor database implemented and accessible to all missions | Yes | All missions have Internet access to the United Nations Global Marketplace to identify potential suppliers registered with the Procurement Service and other United Nations organizations |

H.	Department of Safety and Security

| Expected accomplishment 1: improved ability of the Secretary-General, the Security Council, the General Assembly, other intergovernmental bodies and troop/police-contributing countries to make fully informed decisions on issues relating to peacekeeping. |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Report to General Assembly on the implementation of recommendations in the report called for in resolution 56/255 to evaluate the relationship and interaction between the Department of Peacekeeping Operations and the Office of the United Nations Security Coordinator, submitted to the Assembly at its fifty-eighth session | No | Report (A/59/332) submitted to the General Assembly at its fifty-ninth session |

| Expected accomplishment 3: increased efficiency and effectiveness in conducting, managing, directing and supporting peacekeeping operations |
| --- |
| Planned outputs | Completed (Number or yes/no) | Remarks |
| Annual peacekeeping mission security compliance assessment visits (UNMEE, UNDOF, UNIFIL, UNMOGIP and UNFICYP) | 4 | ONUB, MINUCI, UNMIL and MONUC visited |
| 5 peacekeeping missions’ security compliance reports | 5 | UNDOF, UNFICYP, UNIFIL, UNMEE and UNOMIG were visited |
| Annual peacekeeping mission security training workshop for chief security officers | 1 | Annual security training for 27 chief security officers |
| Security training for mission security management teams (UNAMSIL, MINUCI, UNMIK, UNMIL, UNOMIG and MONUC) | Yes | For an average of 20 staff members each in UNAMSIL, MINUCI, UNMIK, UNMIL, UNOMIG and MONUC |
| Security CD-ROM developed for use by Department of Peacekeeping Operations staff members | Yes | The CD-ROM is now finished and in use |
| 150 security personnel are screened | 457 | Higher number owing to the need for recruitment of additional officers |
| Pre-screened emergency response teams and prepared standby arrangements | 2 | Emergency response teams were screened (Pakistan, Abidjan) 1 standby team (MINUSTAH) was established |
| Standard operating procedure developed for peacekeeping mission stress counselling units | Yes | The standard operating procedures (3) were created for, substance abuse, critical stress management, and strategic framework for the implementation of psychosocial support |
| Psychosocial support provided to peacekeeping mission civilian staff | Yes | Psychosocial support was provided to 853 staff members |
| Trained 200 mission security and safety personnel and first-line officers, supervisors and managers in physical security surveys, interpersonal skills, operational planning, risk assessment, firearms, VIP protection, personal security awareness, incident command system, baton or night-stick, use of force continuum and general security duties in UNOMIG, UNMIK, UNMISET, UNMIL, MONUC, UNMEE and UNAMSIL | 277 | Trained at MONUC, UNAMSIL, UNMISET, MINUSTAH, UNMIK and UNOCI |
| Conducted after-training inspections and assessment of mission training programme; reviewed safety and security standards; and updated security and safety procedures at UNOMIG, UNMIK, UNMISET, UNMIL, MONUC, UNMEE and UNAMSIL | No | Owing to the peak in recruitment of safety and security standards headquarters security officers in 2005 (200 security officers) and the resulting extraordinary strain on training resources. The situation reverting to normal, completion is expected during the 2005/06 reporting period |